## Sheet1
Sr. No. | Task | Status | Approximate Time to spend | Deadline Date | Investigation Docs | Owner
Linux Internals
1 | ROM code, MLO and u-boot code | In Progress | 1.5 week | 15/9/2013 | 1. https://docs.google.com/presentation/d/1PDyYPoyTkMYYYSyORrZfNZE2ObE-ZMBD1aEsNbce3II/edit#slide=id.p; 2. https://docs.google.com/presentation/d/1v_6cJVC91y54RH_CqxoT5oNj9LZHfi0PWXLwph7H_WM/edit#slide=id.g11aaf413d_022 | Dishendra
2 | Linux Booting Sequence | In Progress | 3 days |  | https://docs.google.com/file/d/1_PmQkgI0WIyaismlshjreh86_pYasDSlOnKPdooLA976ug5fpaEd29hCraHH/edit?usp=sharing | Manish
3 | Memory Management | Start date : 8/9/2013 | 1 week |  |  | Dishendra
4 | Interrupt handling in Linux | In Progress | 1 week |  |  | Manish
5 | Kernel Synchronization Techniques | In Progress | 1 week |  |  | Manish
6 | System calls with examples | Start date : 8/9/2013 | 2 days |  | https://docs.google.com/presentation/d/1ucmxn6qHROLx8S6ck5C_h2111C0yYt0zrd2HotGgG90/edit#slide=id.p | Dishendra
7 | TImers and Time Management
8 | Device and Modules ( Kobjects, ksets and ktypes) |  |  |  |  | Dishendra
9 | Debugging mechanism in Kernel | start date : 16/09/2013 | 1 week | 22/09/2013 |  | Rohit
11 | U-Boot | Done/Pushed to git |  |  |  | Manish
12 | Cache | Done/Pushed to git |  |  |  | Manish
13 | Processes Vs Threads
14 | Linux Scheduler | In Progress |  |  |  | Manish
15 | Kernel Data Structures